## Doc-Control
Version And Change History
Version History | [6 empty] | Change History
Version | Author Name | Date | Reviewer Name | Date | Approver Name | Approved Date | Reason for change | Change Description
0.1 | Clover Connect | 2018-10-09 | Project Lead |  |  |  | Document Created | Initiation
1 | Team Lead | 2018-11-15 | Senior Manager |  |  |  | Document Created | NA
1.1 | Team Lead | 2018-11-15 | Senior Manager | 2018-11-20 | Senior Manager | 2018-11-20 | Document Updated | Communication Plan updated
1.2 | Team Lead | 2018-12-03 | Senior Manager | 2019-01-04 | Senior Manager | 2019-01-04 | Document Updated | Service Level Management updated with removing backup policy and site documents
1.3 | Team Lead | 2019-02-08 | Senior Manager | 2019-02-08 | Senior Manager | 2019-02-11 | Document Updated | Escalation matrix changed
1.4 | Team Lead | 2019-07-31 | Senior Manager | 2019-07-31 | Senior Manager | 2019-07-31 | Document Updated | Availability Management changed
1.5 | Team Lead | 2019-11-21 | Senior Manager | 2019-11-21 | Senior Manager | 2019-11-21 | Document Updated | CSI Plan updated

## Plan
1 | Scope (Mention the services which are in scope and which are out of scope.)
Service in Scope: Oracle Services, Server Monitoring, Proactive alerts, Uptime Management, Space Management, Performance Management, Resource Management, Fault Management, Patch Management, SR Management, Security Management, Backup and Recovery Management
2 | Brief description (Describe the services offered.)
We provide support service for Oracle core DBA application stack only. i.e. to maintain database availability, apply patches, monitor the database, Keep it up and running.
3 | Support window(Include something on the lines of 24 X 7 or 16 X 5, specifying the times, time zones, and days of the week when support is provided.)
24 X 7
4 | List of activities(List each and every activity that comes in as a part of the service.)
1. Monitoring a. Checking Mount point & tablespace free space b. Checking invalid objects. c. Providing log files d. Job status e. DR sync status 2. Database Cloning /Refresh 3. Database Upgrade 4. Shrinking Alert Log & Listener Log 5. Monitoring Hit Ratios
5 | Effort and resources(The total effort required to keep the services up and running and the resources in terms of servers, licenses, etc. should be spelled out. If required, budgets can also be specified.)
4 consultants (Dedicated)for oracle technology are required to support 24*7 business operations.
6 | Team chart and escalation matrix
Clover:
Level 1: Clover Connect Team Level 2: Project Lead Level 3:Senior Manager Level 4: Head of delivery(VP)
Client:
Level 1 :Selvama Level 2:Saravanakumar
Manager
Level 2
Senior Manager
7.0 | SLA
Column1 | Column2 | Column3
Severity | Response Time | Resolution Time
1 | 30 Min | 4 hours
2 | 2 hours | 8 hours
3 | 4 hours | 48 Hours
8.0 | Communication Plan(Mention routine customer communication & internal communication (in terms of status reports, meetings & their frequency)
Sign-off for activities/support requests, if not received within 5 working days will be considered as 'Deemed confirmed'. Team sends/receives email to Client and internally as a part of formal communication. Daily Reports are shared over mail. Plan of action is shared for any major activity. Minutes of Meeting are shared after every meeting. Monthly service report
9.0 | Training Plan(Identify trainings as required)
Performance tuning, Best Practises , Standby configuration, Support/site training for new resources, email etiquttes , soft skill

## Service Level Management
Type Of Service | Oracle DBA
Contract Period | Jan 2019 to Dec 2019
Mode of Delivery | Remote Support
Service Window | Monday to Sunday 24 X 7
Locations | Clover Office, Mumbai
Issue Type | Response Time | Resolution Time
Severity 1 | 30 Min | 4 hours
Severity 2 | 2 hours | 8 hours
Severity 3 | 4 hours | 48 Hours
Scope / Deliverables | Description | Frequency | Targets / Thresholds | Documents and Reports
Server Monitoring | Consultant will be monitoring key areas to minimize issues with Oracle Infrastructure. Examine environment to detect issues and make necessary recommendations to improve overall performance, Periodic Housekeeping of logs and trace files | Daily | NA | Health check list
Uptime Management | Primary responsibility to reduce unplanned downtime. The same will be done by: 1. Daily monitoring and alerts. 2. Ensure backup strategy in place. The information on the same should be readily available. 3. Plan for recovery in case of failure and ensure minimum downtime | Daily | NA | Health check list
Space Management | Defining and monitoring threshold values for individual database growth. Monitoring the same Monitor system and database for space availability, w.r.t. Disk capacity. No Application Outages due to space crunch. | Daily | NA | Health check list
Resource Management | Monitoring system utilization and parameters. (e.g) user limit, process limits etc. Ensure no database/Application Outages. | Daily | NA | Part of Health Check List
Fault Management | Monitor log files for error, warning and alerts. Resolution for errors and warnings which could affect performance. | Daily | NA | Health check list
Patch Management | Apply patches initially on a test environments before finally applying on the production environment. ATS (Oracle – Annual Technical Support) is a prerequisite | As when required | NA | Detailed Activity Report
Service Request (SR) Management | Assistance in raising service request to Oracle ATS (Oracle – Annual Technical Support) is a prerequisite In case of severity – I SR raised to Oracle, will ensure the Oracle recommendations are initiated immediately once the SR update | As when required | NA | Through Oracle Meta-link
Backup & Recovery management | Backup and recovery Policy 1. Designing backup and recovery Policy for the site. 2. Ensuring the back-up is done as defined in the Backup 3. Contingency test for backup as scheduled | Once a year | NA | Backup Policy Document
Documents | Detailed documentation of entire Oracle instance and server 1. Site documentation | Once a year | NA | Site Documentation
Reports | Detailed activity report for every planned activity The report will be submitted to the client on completion of activities, Monthly Service Report MSR will be sent to client every month | As and when required, Monthly | NA | Monthly Service Report (MSR)
On Request Activities | Software installations and database creation, 1. Refreshing or rebuilding test Environment. User /Object Creation Should be done only with due approval by way of Change request form Upgradation to latest new release | As per request | NA | Detailed Activity Report

## Capacity Management
Sr No | Area/Item Monitored | Capacity Requirements | % Increase Needed Per <time period> | Capacity Threshold(s) | Threshold Response Strategy (Action to Be Take Upon Reaching Threshold(s))
1 | Disk Space | optimal | as per db growth | 90% | mails raised separate apart from DCH,
2 | RAM | optimal | as per db growth | 20-30% idle | mails raised separate apart from DCH,

## Availability Management
Sr. No. | Service name | Service Owner | Technical Lead | Area of Improvement | Description of the measure | Target values for the Availability to be achieved | Target date | Status
1 | Oracle core DB | Senior Manager | Project Lead | Business Continuity | DR in place | 100 % availabiilty of database (DR Server Banglore) | Done | complete
2 | Oracle core DB | Senior Manager | Project Lead | Business Continuity | Unavaialbilty of site | 100% availabiilty to database server through remote session | Done | Completed

## Configuration Management
Sr. No | CI Code | Name | CI type | CI owner | Manufacturer information | Version information | Location | Modification history of the CI Record | Status history | Relationships to other CIs | Document references
1 | CI001 | Service Management Plan | Document | Project Lead | Clover InfoTech | V1.3 | Mumbai-DMS | 09/10/2018 | Current | NA | Alfresco
2 | CI002 | Problem and Known Error | Document | Project Lead | Clover InfoTech | V1.0 | Mumbai-DMS | 09/10/2019 | Current | NA | Alfresco
3 | CI004 | Backup Policy | Document | Project Lead | Clover InfoTech | V1.0_y18-19 | Mumbai-DMS | 30/07/ 2018 | Current | NA | Alfresco
4 | CI005 | Site Document | Document | Project Lead | Clover InfoTech | V1.0_y18-19 | Mumbai-DMS | 30/07/ 2018 | Current | NA | Alfresco
`

## Change Management
CR No | CR Date | Change Description | Priority | Approved by | Person Responsible | Start Date | End Date | Present status
CR Done by client

## Release Management
Release No | Change Request No, If any | Release Type | Description | Approval status | Priority | Person Responsible | Planned start date | Planned end date | Release deployed date | Roll back activity (If requitred)
RM Done by client

## Service Continuity Management
Refer Risk Management Plan
| Identified non-tolerable risks |  | Measure for reducing/ eliminating the risk
Sr. No | Name of the risk | Affected IT Services | Description | Efforts and Resource | Person Responsible | Target date | Status

## RiskLog
Risks |  |  |  |  | Refer Risk Management Plan
Identification |  |  |  | Analysis |  |  | Mitigation Action
Risk No | Category* | Description | Owner | Impact** | Probability*** | Priority | Plan | Responsibility | Date | Status
| * Category | Requirement, Design, Technology, Integration, Schedule, Resource, Skills, Deployment and support, Business, Maintenance and enhancement
| **Impact | H - High : Risks not under control, affects the project adversely in terms of cost and schedule
M - Medium: Risks under control, affects the project adversely in terms of cost and schedule
L - Low : Risks which do not affect the project adversely in terms of cost and schedule
| ***Probability | H - High : Probability of risk occurrence is >= 60%
M - Medium: Probability of risk occurrence is between 30% and 59%
L - Low : Probability of risk occurrence is < 29%
| Note | Risks that requires mitigation action planning 1 High impact and High probability 2 High impact and Medium probability 3 Medium impact and High probability

## CSI Plan
Sr. No | Process or service | Description | Person Responsible | Priority | Source | Approval | Business case | Implementation schedule
1 | Oracle remote | Backup contingency test should be performed on quarterly basis for all Production database backups, to ensure backup validity. | Blue Dart | high | Backup Validation | Blue Dart | Backup availability | quarterly
2 | Oracle remote | DR Drill activity should be preform to check dr reediness incase of any issue with production database. | Blue Dart | high | DR readiness | Blue Dart | DR readiness | quarterly