## Issue Log
Bluedart
Server | INSTANCE | ACTIVITY | Raised By | Consultant | SEVERITY | RECEIVED | RESPONDED | RESOLVED | STATUS | Pending On | Remarks | Responded Difference | Resolved Difference
[6 empty] | Date & Time | Date & Time | Date & Time
172.18.1.21 | BRMSUAT | brms uat instance 12c on 1.21 | Dinesh | Rohan S | S2 | 2019-11-05 17:01 | 2019-11-05 17:10 | 2019-11-05 18:00 | Done | N.A |  | 0:09 | 0:59 | 1 | 1
172.18.1.21 | BRMSUAT | new brmsuat instance | Dinesh | Rohan S | S2 | 2019-11-05 16:51 | 2019-11-05 17:25 | 2019-11-05 20:21 | Done | N.A |  | 0:34 | 3:30 | 1 | 1
172.21.100.25 | BLUEDARTDR | DR failover test | Dinesh | Siraj | S2 | 2019-11-07 16:30 | 2019-11-07 16:37 | 2019-11-07 19:17 | Done | N.A |  | 0:06 | 2:47 | 1 | 1
172.18.62.105 | C2pc Dev | EXPORt Table | Dinesh | Rohan S | S2 | 2019-11-08 12:10 | 2019-11-08 12:12 | 2019-11-08 13:10 | Done | N.A |  | 0:02 | 1:00 | 1 | 1
172.18.1.45 | Bluedart | Export BRMSUSER_UAT schema and import in bluedart database. | Dinesh | Vishal K | S2 | 2019-11-09 04:10 | 2019-11-09 06:00 | 2019-11-09 07:10 | Done | N.A |  | 1:50 | 3:00 | 1 | 1
172.18.62.105 | C2pc Dev | C2PC Development Database Cleanup | Dinesh | Siraj F | S2 | 2019-11-10 10:03 | 2019-11-10 10:08 | 2019-11-10 12:08 | Done | N.A |  | 0:05 | 2:05 | 1 | 1
172.18.1.45 | Bluedart | full export and conditional import on bluedart sunday 1500 | Dinesh | Prathamesh | S2 | 2019-11-10 11:36 | 2019-11-10 13:16 | 2019-11-10 15:16 | Done | N.A |  | 1:40 | 3:40 | 1 | 1
172.18.1.21 | Bluetest | Metadata backup | Dinesh | Amit | S2 | 2019-11-11 11:36 | 2019-11-11 11:41 | 2019-11-11 12:06 | Done | N.A |  | 0:05 | 0:30 | 1 | 1
172.18.62.104 | c2pcdev | C2PC Development Database Backup-Meta Data | Dinesh | Priya | S2 | 2019-11-12 11:49 | 2019-11-12 12:31 | 2019-11-12 12:43 | Done | N.A |  | 0:42 | 0:54 | 1 | 1
172.18.62.105/39 | C2PC DEV | backup of all schemas for central and Web logic database | Dinesh | Priya | S2 | 2019-11-13 12:16 | 2019-11-13 12:31 | 2019-11-13 12:59 | Done | N.A |  | 0:15 | 0:43 | 1 | 1
172.18.1.45 | Bluedart/ Actuate | restart of BLUEDART and ACTUATE database | Dinesh | Ashish Shinde | S2 | 2019-11-17 12:01 | 2019-11-17 12:16 | 2019-11-17 18:19 | Done | N.A |  | 0:15 | 6:18 | 1 | 1
172.18.1.45 | Actuate | move the indexes from CUSTDSS2009 tablespace to ACTU_INDEX1 tablespace | Dinesh | Ashish Shinde | S2 | 2019-11-18 19:01 | 2019-11-18 19:16 | 2019-11-18 20:34 | Done | N.A |  | 0:15 | 1:33 | 1 | 1
172.18.1.45 | Actuate | online rebuild attached index in FACTDATA1 tablespace | Dinesh | Siraj | S2 | 2019-11-20 20:16 | 2019-11-20 20:36 | 2019-11-20 21:03 | Done | N.A |  | 0:20 | 0:47 | 1 | 1
172.18.111.152 | Webdb | WEBPORTAL1 schema on webdb | Dinesh | Priya | S2 | 2019-11-21 09:46 | 2019-11-21 10:19 | 2019-11-21 12:12 | Done | N.A |  | 0:34 | 2:26 | 1 | 1
172.18.111.152 | Webdb | webdb online index rebuild on sunday at 1430hrs | Dinesh | Vishal Kesarkar | S3 | 2019-11-21 12:56 | 2019-11-21 13:01 | 2019-11-24 18:46 | Done | N.A |  | 0:05 | 77:50 | 1
172.18.111.152 | Webdb | dr_web listener log | Dinesh | Siraj F | S2 | 2019-11-21 14:09 | 2019-11-21 14:41 | 2019-11-21 14:45 | Done | N.A |  | 0:32 | 0:36 | 1 | 1
172.18.1.45 | Bluedart | Monthly export of bluedatdba tables on bluedart tonight after 0930pm | Dinesh | Siraj | S3 | 2019-11-22 15:52 | 2019-11-22 15:58 | 2019-11-22 23:08 | Done | N.A |  | 0:06 | 7:16 | 1 | 1
172.18.1.21 | BRMSUAT | export of brmsuser schema tables & import of brmsuat@172.18.1.21 | Dinesh | Amit | S3 | 2019-11-24 19:12 | 2019-11-24 19:18 | 2019-11-25 05:21 | Done | N.A |  | 0:06 | 10:09 | 1 | 1
172.18.61.26 | OEM | alerts to be disabled NEW_DTC | Dinesh | Amit | S2 | 2019-11-25 10:40 | 2019-11-25 11:07 | 2019-11-25 12:37 | Done | N.A |  | 0:27 | 1:57 | 1 | 1
172.18.100.244 | C2PC | C2PC Production Database:OEM alert of 12th august reporting repetitively | Darshana | Priya P | S2 | 2019-11-27 11:40 | 2019-11-27 12:10 | 2019-11-27 12:25 | Done |  |  | 0:30 | 0:45 | 1 | 1
172.18.1.45 | Actuate | INDEX Rebuilding on actuate | Dinesh | Rohan S | S2 | 2019-11-30 19:16 | 2019-11-30 19:46 | 2019-11-30 23:12 | Done |  |  | 0:30 | 3:56 | 1 | 1
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE
[14 empty] | FALSE | FALSE

## Dashboard
Severity | Issues | Responded |  |  |  | Resolved
|  | Responded | Average Time of Responded | Responded SLA% | On Time SLA % | Resolved | Average Time of Resolved | Resolved SLA % | On Time SLA % | Severity | Responded | Resolved
S1 | 0 | 0 | - | - | - | 0 | - | - | - | S1 | 30 | 240
S2 | 18 | 18 | 0:29 | 100% | 100% | 18 | 2:05 | 100% | 100% | S2 | 240 | 480
S3 | 3 | 3 | 0:06 | 100% | 100% | 3 | 31:45 | 100% | 66.67% | S3 | 480 | 2880
S4 | 0 | 0 | - | - | - | 0 | - | - | - | S4 | 480 | 2880
Overall | 21 | 21 | 0:26 | 100% | 100% | 21 | 6:19 | 100% | 95.24%