## Summary
Form : Project Status Report
Project Name | Oracle Database Support | Project ID | I18ODM003 | Project Life-cycle | Managed IT Services | Project Life-cycle
Group | BAU Infra Delivery |  |  |  |  | Managed IT Services
Project Dates |  | Start Date | 2019-01-01 | End Date | 2019-12-31 | Infrastructure Project Delivery - Upgrade
Customer's Organization | ***** (Project Name) |  |  |  |  | Infrastructure Project Delivery - Integration
Current Phases | Support |  |  | Date of Reporting | 2019-12-08 | Application Development
Project Manager | Vinod Nair |  |  | Delivery Head | Siddharth Deshmukh | Infrastructure Project Delivery - Implementation
Reporting Month | 2019-11-01 |  |  | Go-live Date | NA | Application Support
Distribution List | Shefali Purav , Vinod Nair , Siddharth Deshmukh,Quality Team
Project Health
Executive Dashboard
Deliverables Performance | Met |  |  |  |  | Group
Issues | Closed |  |  |  |  | BAU App Delivery
Schedule Performance | On Time |  |  |  |  | BAU Infra Delivery
Risks | Under Control |  |  |  |  | Practice Infra Delivery
Practice App Delivery
Summary
Please Enter the health of the project in 4 to 5 lines
Database monitoring of Priamry and DR database.
Tablespace,Disk space monitoring on daily basis
Alert Monitoring
DR recovery
Database Backup checking

## Project Status
Form : Monthly Project Status Report
Project Name |  | Oracle Database Support |  | Project ID | I18ODM003
Group |  | BAU Infra Delivery
Project Dates |  |  |  | Start Date | 2019-01-01 | End Date | 2019-12-31
Customer's Organization |  | ***** (Project Name)
Current Phases |  | Support |  |  |  | Date of Reporting | 2019-12-08
Project Manager |  | Vinod Nair |  |  |  | Delivery Head | Siddharth Deshmukh
Reporting Month |  | 2019-11-01 |  |  |  | Go-live Date | NA
Distribution List |  | Shefali Purav , Vinod Nair , Siddharth Deshmukh,Quality Team
Project Status
A. Deliverables
Sr. No. | Description | Date | Responsibility | Status | Remarks
1 | Database monitoring of Priamry and DR database. | Daily | CIPL | On Going | NA
2 | Tablespace,Disk space monitoring on daily basis | Daily | CIPL | On Going | NA
3 | Alert Monitoring | Daily | CIPL | On Going | NA
4 | Database ,Schema Refresh | On request | CIPL | On Going | NA
5 | DR drill | On request | CIPL | On Going | NA
6 | Database backups and restoration | On request | CIPL | On Going | NA
B. Milestones Targeted for the period
Sr. No. | Milestones | Responsibility |  | Status | Remarks
NA | NA | NA | NA | NA | NA
[State the milestones for the stated period]
C. Issues
Sr. No. | Description | Responsibility | Resolve by Date | Requires Management Attention Y /N | Internal / External
NA | NA | NA | NA | N | NA
[Any problems / issues to be resolved should be described here]
D. Process Compliance Index
Month | PCI | Remarks
2018-11-01 | 94.29% | Completed
2018-12-18 | 100% | Completed
2019-01-18 | 98.61% | Completed
2019-02-18 | 97.5% | Completed
2019-03-18 | 100% | Completed
2019-04-18 | 85% | Completed
2019-05-18 | 100% | Completed
2019-06-19 | 85% | Completed
2019-07-19 | 97.5% | Completed
2019-08-19 | 97.5% | Completed
2019-09-19 | 93.75% | Completed
2019-11-19 | 93.75% | Completed
E. Significant Learning's / Intellectual Property
Month | Year | Intellectual property | Lessons Learned / Brief Description | Owner | Category | Status | Comments
Sep |  | Intellectual Property | Proactive communication to be proper | CIPL | Quality improvement | In Process | NA
Oct |  | Intellectual Property | Ontime updates of every activity | CIPL | Quality improvement | In Process | NA
Nov |  | Intellectual Property | NA | NA | NA | NA | NA
Dec |  | Intellectual Property | NA | NA | NA | NA | NA
F. Significant Value Add / Innovation
Sr No. | Month | Year | Value Add / Innovation | Brief Description | Business Impact | Recommendation | Benefit | Comments
| Sep |  |  | NA | NA | NA | NA | NA
| Oct |  |  | NA | NA | NA | NA | NA
| Oct |  |  | NA | NA | NA | NA | NA
G. Reuse Assets
No of reusable components planned to create | No of reusable components created | No. of components planned to reuse | No. of components reused | % Reuse of the project | Effort savings in hours | Cost Savings (₹) | No of reusable components contributed to Asset Manager | Provide Action Tracker Reference Nos
NA | NA | NA | NA | NA | NA | NA | NA | NA

## Risks
Form : Monthly Project Status Report
Project Name |  | Oracle Database Support |  | Project ID | I18ODM003
Group |  | BAU Infra Delivery
Project Dates |  |  |  | Start Date | 2019-01-01 | End Date | 2019-12-31
Customer's Organization |  | ***** (Project Name)
Current Phases |  | Support |  |  |  | Date of Reporting | 2019-12-08
Project Manager |  | Vinod Nair |  |  |  | Delivery Head | Siddharth Deshmukh
Reporting Month |  | 2019-11-01 |  |  |  | Go-live Date | NA
Distribution List |  | Shefali Purav , Vinod Nair , Siddharth Deshmukh,Quality Team
Risks
Risks : Internal
Identification |  |  | Analysis |  | RPN Value | Risk Status | Mitigation | Action
Risk No | Category* | Description | Impact** | Probability*** |  |  |  | Plan | Responsibility | Date | Status
1 | Resource | Customer concerns over frequent resource changing which affects support standards | Medium | Medium | 16 | Closed | Customer should be informed for resource changing | Handover should be completed to alternate resource | Project Leader | NA | Complete |  |  |  |  | MediumMedium | #N/A | High | High | HighHigh | A
2 | Technology | Cloverconnect email ID which was common for EBS and Oracle teams hangs and slow email fetch , imapcts response time | Medium | Low | 8 | Closed | Created EBS Email ID separetly to reduce concurrency | Created EBS Email ID separetly to reduce concurrency | Project Leader | NA | Complete | Impact | Value | Probability | Value | MediumLow | #N/A | High | Medium | HighMedium | B
3 | Skills | L1 resources come from academy with no exposure on production evviornment | High | Low | 16 | Closed | L1 resources to be given devopement access and then move on production | hire external resources with basic exposure to production enviornment | Project Manager | 2018-12-01 | Complete | High | 8 | High | 8 | HighLow | #N/A | High | Low | HighLow | C
[5 empty] | 0 | [6 empty] | Medium | 4 | Medium | 4 |  | #N/A | Medium | High | MediumHigh | D
[5 empty] | 0 | [6 empty] | Low | 2 | Low | 2 |  | #N/A | Medium | Medium | MediumMedium | E
[5 empty] | 0 | [11 empty] | #N/A | Medium | Low | MediumLow | F
[18 empty] | Low | High | LowHigh | G
[18 empty] | Low | Medium | LowMedium | H
Risks : Customer Related | [17 empty] | Low | Low | LowLow | I
Identification |  |  | Analysis |  | RPN Value | Risk Status | Mitigation | Action
Risk No | Category* | Description | Impact** | Probability*** |  |  |  | Plan | Responsibility | Date | Status
1 | Technology | Customer not augmenting their Infrastructure | Medium | Medium | 16 | Closed | realignment of SLAs based on the infrastructre available | realignment of SLAs based on the infrastructre available | Client Manager | NA | Complete |  |  |  |  | MediumMedium | #N/A
2 | Network | DR sync issue due to network slowness | Medium | Medium | 16 | Closed | need to copy archive logs o DR manually | upgrade network | Client Manager | 2018-11-01 | Complete |  |  |  |  | MediumMedium | #N/A
3 | Technology | Oracle Database in lower version(10.2.0.5) where many issues faced due to some BUGS | Medium | Low | 8 | Closed | Altrnative solutions provided by oracle | Upgrade database to latest version | Client Manager | 2018-12-01 | Complete
4 | Technology | Backup contegency test | Medium | Medium | 16 | Closed | Backup must restore on Dr for testing | Full backup must be send on dr site to test full tape level backup. | Client Manager | 2019-01-01 | Complete |  |  |  |  | MediumMedium | #N/A
* Category (e.g.) | Requirement, Design, Technology, Integration, Schedule, Resource, Skills, Deployment and support, Business, Maintenance and enhancement
**Impact | H - High : Risks not under control, affects the project adversely in terms of cost and schedule
M - Medium: Risks under control, affects the project adversely in terms of cost and schedule
L - Low : Risks which do not affect the project adversely in terms of cost and schedule
***Probability | H - High : Probability of risk occurrence is >= 60%
M - Medium: Probability of risk occurrence is between 30% and 59%
L - Low : Probability of risk occurrence is < 29%
Note on A24: Insert Row Above this
Note on A33: Insert Row Above this

## Proj Mgmt Measures
Form : Monthly Project Status Report
Project Name |  | Oracle Database Support |  | Project ID | I18ODM003
Group |  | BAU Infra Delivery
Project Dates |  |  |  | Start Date | 2019-01-01 | End Date | 2019-12-31
Customer's Organization |  | ***** (Project Name)
Current Phases |  | Support |  |  |  | Date of Reporting | 2019-12-08
Project Manager |  | Vinod Nair |  |  |  | Delivery Head | Siddharth Deshmukh
Reporting Month |  | 2019-11-01 |  |  |  | Go-live Date | NA
Distribution List |  | Shefali Purav , Vinod Nair , Siddharth Deshmukh,Quality Team
Measures and Metrics For the Month - Sep-19
| Month |  |  | Mmm-yy
| Objective | Target | Responsibility | Deliverable/Milestone | estimated end | Actual end | Variance
| Schedule Variance | 90% | PM | NA | NA | NA | #VALUE!
| Objective | Target | Responsibility | Deliverable/Milestone | Estimated Effort | Actual effort | Variance
| Effort Variance | 85% | PM | NA | NA | NA | #VALUE!
| Month |  |  |  | Nov-19
| Objective | Frequency | Responsibility | Target | Actual
| Number of Critical Defects | Monthly | PM | </=2 | NA
| Testing Iterations | Monthly | PM | </=3 | NA
| PCR Index | Monthly | PM | 70% | 93.75%
| Customer Satisfaction | Yearly | PM | >/=3 | Waiting for feedback from client

## App Supp Measures
Form : Monthly Project Status Report
Project Name |  | Oracle Database Support |  | Project ID | I18ODM003
Group |  | BAU Infra Delivery
Project Dates |  |  |  | Start Date | 2019-01-01 | End Date | 2019-12-31
Customer's Organization |  | ***** (Project Name)
Current Phases |  | Support |  |  |  | Date of Reporting | 2019-12-08
Project Manager |  | Vinod Nair |  |  |  | Delivery Head | Siddharth Deshmukh
Reporting Month |  | 2019-11-01 |  |  |  | Go-live Date | NA
Distribution List |  | Shefali Purav , Vinod Nair , Siddharth Deshmukh,Quality Team
Measures and Metrics For the Month - Mmm-YY
Not Applicable
| Month |  |  |  | Mmm-yy
| Objective | Frequency | Responsibility | Target | Actual
| Achieve Internal/External SLA Parameter | Monthly | Project Manager / Project Lead | 85%
| CSAT | Half Yearly | Project Manager | >=3
| Reduction in defect count | Monthly | Project Lead | <2

## Managed Service Measures
Form : Monthly Project Status Report
Project Name |  | Oracle Database Support |  | Project ID | I18ODM003
Group |  | BAU Infra Delivery
Project Dates |  |  |  | Start Date | 2019-01-01 | End Date | 2019-12-31
Customer's Organization |  | ***** (Project Name)
Current Phases |  | Support |  |  |  | Date of Reporting | 2019-12-08
Project Manager |  | Vinod Nair |  |  |  | Delivery Head | Siddharth Deshmukh
Reporting Month |  | 2019-11-01 |  |  |  | Go-live Date | NA
Distribution List |  | Shefali Purav , Vinod Nair , Siddharth Deshmukh,Quality Team
Measures and Metrics For the Month - Nov-19
| Month |  |  |  | Nov-19
| Objective | Frequency | Responsibility | Target | Actual
| Achieve Internal/External SLA Parameter | Monthly | Project Manager / Project Lead | 85% | 95%
| Reduce Resource attrition | Quarterly | Project Manager / Project Lead | 5% | 0%
| CSAT | Half Yearly | Project Manager | >=3 | Waiting for feedback from client