## Issues
<Project Name> - Issue Log
Item | Application | Creation Date | Originator | Description | Symptom | Actions being taken | Risk | Solution/Recommendation | Date Closed | Status | Priority | Follow-up Action | UAT1 Discovered | review after patch set insatll | Resolved By
1 | GL / ALL | 2014-03-11 | Stefano | Subaccount segment definition | Table name of Value set is wrong | Updated the table name in value set definition and recompile the value set. |  |  | 2014-03-11 | Closed | medium |  |  |  | Technical Team
2 | AR | 2014-03-11 | Stefano | FOR A2F023 | FOR A2F023 Compltes with error | Changed the Valueset. Report is working. |  |  | 2014-03-14 | Closed | Medium
4 | AR | 2014-03-11 | Stefano | XXE: RPT-A2F-0023 AR Customer Credit Profile Information | Report Missing from Receivables All reuqest group (other custom reports are in the req group) Why this particular report is not in the reuqest group? Other reports may be missing form the re. groups? | Attached report to responsibility group Receivables All |  | Due to upgradation or post upgradation patches, report attachment may lost. | 2014-03-12 | Closed | medium | Check systemo for more missing reports |  |  | Technical Team
7 | AR | 2014-03-11 | Stefano | Error while querying an AR invoice in USD | The system cannot determine geographical information for this location and cannot derive a tax juridiction. Please contact your system administrator | I am currenctly the issue it may be set up issue |  | Not able to reproduce the issue. Need details |  | Closed | medium | Functional issue
8 | Custom | 2014-03-11 | Renata | custom.pll | log off and log in and tries to open Material workbench or ORG item view, system displayed error. Check. Screenshot | Recreated the xxp_custom.pll attached to custom.pll and compiled custom.pll again. |  |  | 2014-03-11 | Closed | High | See 18 |  |  | Technical Team