## Defects
			Defect Report for Clover QMS

			0
Test Environment:		DEV

Defect #	Defect Logged Date	User ID & Password	Description of the Defect	Steps to reproduce Defect	Defect Screenshot Link	Defect Type	Severity	Priority	Defect Status	Retesting Defect Status	Close Date	Defect Age
QMS-01	19/09/2022	CI2269	After Click on customer master ,View Feedback and Raise Form module, the title name should be appear in center alignment of the screen.	1.open http://192.168.2.107:8088/User/Login / 2.Customer>>Customer Master / 3.Title of module	#Snapshot1	UI	Medium	P2	Fixed
QMS-02	19/09/2022	CI2269	Refresh button is not working	1.open http://192.168.2.107:8088/User/Login / 2.Customer>>Customer Master / 3.Search Data / 4.Refresh	#Snapshot2	Functional	Medium	P2	open
QMS-03	19/09/2022	CI2269	Customer 2 Name ,Customer 3 Name,Customer 4 Name,Customer 2 Email,Customer 3 Email,Customer 4 Email,Customer 2 designation,Customer 3 designation,Customer 4 designation / These fields are not mandatory while adding customer.	1.open http://192.168.2.107:8088/User/Login / 2.Customer>>Customer Master / 3.Add	#Snapshot3	Functional	Medium	P2	Fixed
QMS-04	19/09/2022	CI2269	All fields are getting mandatory while edit records. / “Only Alphabets allowed.” this validation is appear after edit record it should be appear while adding record.	1.open http://192.168.2.107:8088/User/Login	#Snapshot4	Functional	Medium	P2	Fixed
QMS-05	19/09/2022	CI2269	Manager Name,Project Manager Emailid,Project Delivery Manager name,Project Delivery Manager emailid,Project Delivery Head name,Project Delivery Head emailid these fileds are not appearing after click on edit button	1.open http://192.168.2.107:8088/User/Login	#Snapshot5	Functional	Medium	P2	Fixed
QMS-06	19/09/2022	CI2269	System should not allow user to add blank customer	1.open http://192.168.2.107:8088/User/Login	#Snapshot6	Functional	Medium	P2	open
QMS-07	19/09/2022	CI2269	After select blank space customer name the proxy error is appear.	1.open http://192.168.2.107:8088/User/Login	#Snapshot7	Functional	Medium	P2	open
QMS-08	19/09/2022	CI2269	After selecting customer master and raise form module the Audit History module tab get highlighted.	1.open http://192.168.2.107:8088/User/Login	#Snapshot8	Functional	Medium	P2	open
QMS-09	19/09/2022	CI2269	After click on Raise button without selecting CHOOSE EMAIL ID dropdown the proxy error is appear.	1.open http://192.168.2.107:8088/User/Login	#Snapshot9	Functional	Medium	P2	Fixed
QMS-10	19/09/2022	CI2269	For Customer 1 user the proxy error is appear after click on Raise button	1.open http://192.168.2.107:8088/User/Login	#Snapshot10	Functional	Medium	P2	open

## Snapshot
QMS 1

QMS 2

QMS 3
Add record

while edit record

QMS 4

QMS 5

QMS 6

QMS 7

QMS 8